## schedule
Task ID | Work Breakdown Structure |  |  |  |  | Planned Start | Planned Finish | Actual Start | Actual Finish | Workload （Plan｜Actual） |  | In Charge | Progress | 2019-01-06 | 2019-01-13 | 2019-01-20 | 2019-01-27 | 2019-02-03 |  | 2019-02-10 | 2019-02-17
id | lv1 | lv2 | lv3 | lv4 | lv5 | plannedStart | plannedFinish | actualStart | actualFinish | plannedWorkload | actualWorkload | responsiblity | progress | [5 empty] | ¦
Assembling Prototype 2 | [11 empty] | Andrew
Set up Knuckles on the plywood base | [5 empty] | 2019-02-04 | 2019-02-07 | 2019-02-04 |  | 10 | 10 | Andrew
Group all wires and organize them in labeled cables | [5 empty] | 2019-02-17 | 2019-02-28 |  |  |  |  | Andrew
Reroute all wires and cables to avoid collisions | [5 empty] | 2019-01-21 | 2019-02-15 | 2019-01-21 |  |  |  | Andrew
3D print new parts | [5 empty] | 2019-01-30 | 2019-04-15 | 2019-01-29 | 2019-04-15 |  |  | Andrew | [6 empty] | ¦
Laser cut the plate for the forearm | [5 empty] | 2019-01-11 | 2019-02-15 |  |  |  |  | Andrew
3D print Camera mount and attach it on Knuckles | [5 empty] | 2019-01-01 | 2019-01-21 | 2019-01-07 | 2019-01-21 |  |  | Andrew
3D print case for microcontroller | [5 empty] | 2019-02-22 | 2019-02-28 |  |  |  |  | Andrew
3D print case for power supplies and stepper drivers | [5 empty] | 2019-02-22 | 2019-02-28 |  |  |  |  | Andrew
Motor and Power Distribution | [11 empty] | Entire Team
Reduce heat in motors using current switches | [5 empty] | 2019-02-11 | 2019-02-15 |  |  |  |  | Entire Team
Recalibrate motors micro steps for smoother motion | [5 empty] | 2019-02-11 | 2019-02-28 | 2019-02-01 |  |  |  | Entire Team
AprilTag Detection | [11 empty] | Matt
Camera detects AprilTag and labels object names on ROS | [5 empty] | 2019-02-11 | 2019-02-17 |  |  |  |  | Matt
Arm follows and centers the tag | [5 empty] | 2019-02-01 | 2019-02-18 | 2019-01-30 |  |  |  | Matt
Maps room and saves locations of AprilTags | [5 empty] | 2019-02-18 | 2019-02-28 |  |  |  |  | Matt
Grabbing and returning objects | [11 empty] | Matt
Receive data input from gripper tactile pads | [5 empty] | 2019-02-28 | 2019-03-08 |  |  |  |  | Matt & Andrew
Robot has a good grip of the arm | [5 empty] | 2019-03-01 | 2019-03-07 |  |  |  |  | Matt
Robot returns to a default position to give an object | [5 empty] | 2019-03-07 | 2019-03-21 |  |  |  |  | Matt
Complete grab and handing in 7 seconds | [5 empty] | 2019-03-19 | 2019-03-30 |  |  |  |  | Matt & Paola
Voice Recognition | [11 empty] | Rym
Link the Intel Development Microphone with Raspberry Pi3+ | [5 empty] | 2019-02-05 | 2019-02-05 | 2019-02-05 |  |  |  | Rym
Link the Intel Raspberry Pi3+ and Amazon Development | [5 empty] | 2019-02-07 | 2019-02-12 | 2019-02-05 |  |  |  | Rym
Retrieve voice to text message from Alexa Voice Service to ROS | [5 empty] | 2019-02-11 | 2019-02-21 | 2019-03-11 |  |  |  | Rym | [6 empty] | ¦
Connect action verb to motion nodes on ROS | [5 empty] | 2019-02-18 | 2019-02-25 | 2019-03-18 |  |  |  | Rym | [6 empty] | ¦
Connect object to the AprilTag node on ROS | [5 empty] | 2019-02-25 | 2019-02-28 | 2019-03-18 |  |  |  | Rym | [6 empty] | ¦
Voice activate Knuckles with "Alexa, Tell Knuckles.." | [5 empty] | 2019-02-28 | 2019-03-20 | 2019-03-18 |  |  |  | Rym | [6 empty] | ¦
GUI | [11 empty] | Paola
Design Template GUI on qtDesigner ROS | [5 empty] | 2019-01-03 | 2019-02-06 | 2019-01-29 | 2019-02-05 |  |  | Paola
List action verbs and objects to be included in Library | [5 empty] | 2019-02-04 | 2019-02-06 | 2019-02-04 | 2019-02-05 |  |  | Paola
Connect GUI to Command Prompt | [5 empty] | 2019-02-07 | 2019-02-13 | 2019-02-06 | 2019-02-07 |  |  | Paola
Connect GUI to Rviz | [5 empty] | 2019-02-14 | 2019-02-21 | 2019-02-07 |  |  |  | Paola
Connect GUI to object detection node | [5 empty] | 2019-02-18 | 2019-02-28 |  |  |  |  | Paola
Execute Commands from the GUI | [5 empty] | 2019-02-25 | 2019-03-07 |  |  |  |  | Paola
Execute Commands from the voice input to the GUI | [5 empty] | 2019-02-28 | 2019-03-06 |  |  |  |  | Paola
Task ID | [11 empty] | In Charge |  | 2019-02-24 | 2019-03-03 | 2019-03-10 | 2019-03-17 | 2019-03-24 |  | 2019-03-31 | 2019-04-07 | 2019-04-14 | 2019-04-21
Assembling Prototype 3 | [11 empty] | Andrew | [7 empty] | ¦
Set up Knuckles on the plywood base | [11 empty] | Andrew | [7 empty] | ¦
Group all wires and organize them in labeled cables | [11 empty] | Andrew | [7 empty] | ¦
Reroute all wires and cables to avoid collisions | [11 empty] | Andrew | [7 empty] | ¦
3D print new parts | [11 empty] | Andrew | [7 empty] | ¦
3D print Camera mount and attach it on Knuckles | [11 empty] | Andrew | [7 empty] | ¦
3D print case for microcontroller | [11 empty] | Andrew | [7 empty] | ¦
3D print case for power supplies and stepper drivers | [11 empty] | Andrew | [7 empty] | ¦
3D print end caps for wires | [11 empty] | Andrew | [7 empty] | ¦
Motor and Power Distribution | [11 empty] | Entire Team | [7 empty] | ¦
Reduce heat in motors using current switches | [11 empty] | Entire Team | [7 empty] | ¦
Recalibrate motors micro steps for smoother motion | [11 empty] | Entire Team | [7 empty] | ¦
AprilTag Detection | [11 empty] | Matt | [7 empty] | ¦
Camera detects AprilTag and labels object names on ROS | [11 empty] | Matt | [7 empty] | ¦
Arm follows and centers the tag | [11 empty] | Matt | [7 empty] | ¦
Maps room and saves locations of AprilTags | [11 empty] | Matt | [7 empty] | ¦
Grabbing and returning objects | [11 empty] | Matt | [7 empty] | ¦
Robot has a good grip of the object | [11 empty] | Matt | [7 empty] | ¦
Robot returns to a default position to give an object | [11 empty] | Matt | [7 empty] | ¦
Complete grab and handing in 7 seconds | [11 empty] | Matt & Paola | [7 empty] | ¦
Voice Recognition | [11 empty] | Rym | [7 empty] | ¦
Link the Intel Development Microphone with Raspberry Pi3+ | [11 empty] | Rym | [7 empty] | ¦
Link the Intel Raspberry Pi3+ and Amazon Development | [11 empty] | Rym | [7 empty] | ¦
Retrieve voice to text message from Alexa Voice Service to ROS | [11 empty] | Rym | [7 empty] | ¦
Connect action verb to motion nodes on ROS | [11 empty] | Rym | [7 empty] | ¦
Create Voice tags for GUI on Python Script | [11 empty] | Rym | [7 empty] | ¦
Voice activate Knuckles with "Alexa, Tell Knuckles.." | [11 empty] | Rym | [7 empty] | ¦
GUI | [11 empty] | Paola | [7 empty] | ¦
Design Template GUI on qtDesigner ROS | [11 empty] | Paola | [7 empty] | ¦
List action verbs and objects to be included in Library | [11 empty] | Paola | [7 empty] | ¦
Connect GUI to Command Prompt | [11 empty] | Paola | [7 empty] | ¦
Connect GUI to object detection node | [11 empty] | Paola | [7 empty] | ¦
Execute Commands from the GUI | [11 empty] | Paola | [7 empty] | ¦
Execute Commands from the voice input to the GUI | [11 empty] | Paola | [7 empty] | ¦