## Sheet1
Have arm be able to retrieve objects for the user, and also can be provided an object and put it down on the desk for the user.
Work fast to get basic functionality working properly (arm moving properly, object detection, voice recognition), and then add features like facial recognition, high fives and waving hello, avoids moving objects and people, chicken head.
Computer vision and neural network, imitation learning, speech recognition and feedback.
Date | Progress | Entire Group | Matthew van Zuilekom | Andrew Blanchard | Rym Benchaabane | Paola Hernandez
October 10th |  |  |  | Pick up cleaning tools from Home Depot
October 12th |  | Get parts from Regina (or at least dates for parts arrival) | Have robot arm track object in simulation | Submit written report by 5PM (ADDIE Design). Ensure Macbook is enough for Rviz/Gazebo robot arm simulation. Clean all components. | Get RealSense camera working on laptop with 2D object detection | 2D object recognition using RealSense Camera
October 19th |  | Build robot. | Pick up parts (fasteners) from Home Depot. | Pick up parts (fasteners) from Home Depot. In SWE conference (October 18th) | 2D object detection reliable and working. Get 2D working well before moving to 3D | 2D object detection reliable and working. Get 2D working well before moving to 3D
October 22nd (Milestone 1) |  | Arm and gripper are fully constructed and functional. All parts printed and parts acquired |  | Buffer
October 23rd |  |  | Presenting in senior design lecture
October 26th |  |  | Gripper and arm in Rviz/Gazebo simulation (finish final CAD of gripper and arm design, convert to URDF, put in Rviz). Recognize shortcomings of Moveo gripper and implement solutions on final gripper | Gripper and arm in Rviz/Gazebo simulation (finish final CAD of gripper and arm design, convert to URDF, put in Rviz). Recognize shortcomings of Moveo gripper and implement solutions on final gripper | Get 3D pointcloud video input showing in Rviz | Submit Progress 1 written report by 5PM. Get 3D pointcloud video input showing in Rviz.
November 2nd |  |  | Print out and assemble final gripper and mount onto arm. Print out camera mount & mount camera on arm | Print out and assemble final gripper and mount onto arm. Print out camera mount & mount camera on arm | 3D object detection | 3D object detection
November 6th |  | Ethics assignment due November 6th at 5PM. Group assignment |  | Buffer | Presenting in senior design lecture
November 9th (Maker Showcase) |  | Arm is fully constructed and moveable/controllable (by controlling the individual motors, not through ROS) | Find and mount tactile pads | Display built arm at Makers' Showcase | Train object detection, can recognize more objects it will most likely encounter | Train object detection, can recognize more objects it will most likely encounter
November 16th |  | Tactile pads respond as expected and recognize when an object has been sufficiently grasped. Gripper lets go when object is pulled on by the user | Submit Progess 2 written report by 5PM. | Order voice kit and microphone. | Fully functional object detection simulation with RealSense working on Rviz. Saves 3D position of the object | Fully functional object detection simulation with RealSense working on Rviz. Saves 3D position of the object
November 20th (Milestone 2) |  | Simulate the final arm/gripper design in Rviz. Arm has all hardware attachments (excluding mic). Camera is working properly in Rviz and providing the saved locations of objects. Tactile pads responding properly and recognize when an object has been grasped. |  | Presenting in senior design lecture
November 21 - 25 |  | Thanksgiving holiday | Buffer | Buffer | Buffer | Buffer
November 27th and 29th |  | Facilitator meetings
November 30th |  |  | Physical arm fully follows simulation seen in Rviz | Physical arm fully follows simulation seen in Rviz | Arm properly responds to text commands | Arm properly responds to text commands
December 1 - 12 |  | Final exams, no classes
December 7th |  |  | Manual control of robotic arm using a controller | Manual control of robotic arm using a controller
December 14th |  | Microphone is able to take audio input and convert to text for voice commands |  |  |  | Out of town
December 21st |  | Arm can remember path made when controlled and duplicate the motion when given the proper text/voice command |  | Out of town
December 28th |  |  | Buffer | Buffer | Buffer | Buffer
December 23 - 30 |  |  | Out of town | Out of town
January 4th |  | Arm can create 3D map of its environment
January 11th |  | Arm can properly locate requested object (via voice command), pick it up and present requested object to user | Redesign base of arm to consolodate and accomodate microphone (based on 6-axis Moveo design) | Redesign base of arm to consolodate and accomodate microphone (based on 6-axis Moveo design) | Arm properly responds to voice commands | Arm properly responds to voice commands
January 14th |  | First day of spring semester | Mount microphone on arm. | Mount microphone on arm.
January 18th |  | Arm can be given an object, and place that object in an empty spot on the table
January 20th (Milestone 3) |  | Implement 3D mapping using RealSense. Simulate object detection and implement on the physical robot. Robot will be able to locate and pick up objects in its environment
February 15th (Milestone 4) |  | Improved object recognition and user position recognition. Implement voice recognition software to accept voice commands |  |  | Fully trained object detection, can recognize every object will most likely encounter. | Fully trained object detection, can recognize every object will most likely encounter.
March 8th (Milestone 6, IEEE Chili Cook off) |  | Implement final voice commands reference library. Robot arm needs to be 100% done! | Eat chilli | Eat chili | Eat chili | Eat chili
March 11th - 17th |  | Spring Break. Prep Robot for travel |  | Birthday Buffer
March 26th (ECEDHA Conference) |  | Demonstrate arm at ECEDHA Conference
April 15th (Milestone 7) |  | Fine tuning based on feedback from IEEE National Conference
Capstone conference date?
April 29 - May 9 |  | Final exams, no classes
What we are trying to achieve, detailed end goal
| Physical robot arm | Object detection
| Assembled robot arm with IEEE gripper. Mounted and functional RealSense, multi-directional microphone, & tactile pads. | 2D object recognition, 3D object detection. RealSense camera can create 3D mapping of environment, detect/recognize objects and save their position. Microphone can detect where a user is and can face user to hand over the object. Tactile pads can sense when an object has been adequatly grasped so arm can move without dropping object, and can also sense when user is pulling on the object.
| Arm needs to move faster than a human assistant, while still keeping object under control | Uses a network to train. Improve object detection and voice recognition
Physical arm follows simulated arm

## Sheet2
Short comings:
1. The arm is horribly depressed